Background

The ??name?? Rogaine will be held from 12:00 noon Saturday ??Saturday date?? to 12:00 noon Sunday ??end date??, 20??.  It is expected that between 400 and 500 competitors and volunteers will be on site for the event.  The actual event will cover some ??area?? square kilometres of the ??location?? State Forest with the Hash House and Administration centre located on  ??hash house location??.  A draft copy of the map is attached, showing the main access roads and the location of the base camp (Hash House).

# Emergency Services

The Western Austrralian Rogaining Association (WARA) has produced a Safety / Search & Rescue - 1st Aid Manual – a copy is maintained on site at all times.  A copy is attached.

Emergency services such as Fire, Hospital and Police have been notified of the Rogaine Event with directions given to the Police and Fire Departments, so that if necessary they can easily find the event site at the ??location of hash site??.   The Emergency Contact numbers and directions to the Rogaine site obtained during the setting / planning of the Rogaine are included at the end of this document.

Competitor Safety

Patrolled Roads

The Rogaine event map contains ???? kms of designated patrolled roads. The idea of these roads being patrolled at regular intervals is one of the prime Risk Management tools of WA Rogaining. Patrol cars driven by the organisers are easily identified by the red “ROGAINE” signage on the windscreens of the cars and “Green” rotating lights to help identify them at night along with luminous safety vests for the organising personal. This strategy was developed over time to help the competitors, both young and old, to identify which cars can be approached (in remote bush settings) with safety especially at night if they are in need of assistance.  Green lights have been selected to avoid confusion with normal emergency vehicles such as police and ambulance.

The patrolled roads are marked on the competitor’s maps, and are

- ??give detailed list of all patrolled roads??

Injury Management

The patrol vehicles are in place to return any competitor that is fatigued or injured to the First Aid Station at the Rogaine base camp. The Administration Team are in constant touch with the Patrol cars via CB Radios and if necessary to contact any emergency service via a Satellite Phone.

The first aid station at the Rogaine base camp is manned for the duration of the event, by someone who has at least Senior First Aid qualifications.

Dehydration Management

All competitors are advised to carry at least 2 litres of water when on the course.  There are ??number?? water drops on the map for competitors to refill their water bottles and these water stations are checked and replenished at regular intervals by the organisers.

In Case of Major Fire

There are approx ??area??square kilometres to the map area and within the map boundaries will be up to 400 competitors at any given time.

Competitors are briefed at the start of the event regarding any possible hazards within the map area with the instruction that due to any emergency they should make their way to the nearest water drop or patrolled road where they will be attended to by the Event Organisers or appropriate Emergency Service personal.

The road entries and boundaries to the map have “NO SHOOTING” signs with warnings that there are up to 400 bush walkers in the area.  Road signage such as 300mtrs, 150mtrs and ROGAINE turn, will aid competitors and service vehicles to navigate with safety in and out of the map area.

Emergency Contacts

Fire

??local?? Volunteer Bush Fire Brigade			??number??

Medical

??local?? Hospital		??address??		??number??

??local?? Ambulance		??address??		??number??

Police

??local?? Police			??address??		??number??

DEC

Contact Officer	(??name??)				??number??

(A/H)				??number??

DEC Office						??number??

Directions to site

- ??provide directions to site as per competitors instructions??

Event Organisers

Further information about this event can be obtained from

Course Setters

Setter name		ph  ?????? (Home)        	?????? (mob)

“address”

Brian Wade		ph  ?????? (home)	?????? (mob)

“address”

DEC reference

An application was made to DEC in ??when??, and preliminary approval granted in ??when??, subject to provision of traffic management and emergency management plans.

DEC Reference   ??????